EVENT CHECKLIST

6-8 Weeks Prior

| Task | Comments | Completed |
| --- | --- | --- |
| Determine goals and purpose of event | - Who is your target audience for the event? - What are your key messages? - What do you hope to accomplish? - How will you gauge effectiveness? - How does this event complement the college & university’s Strategic Plan? |  |
| Select date and time | - Ensure hosts, VIPs, and/or speakers are available for specified dates - Department/center responsibility* - Consult college/campus event calendars - Consult speaker schedules/availability |  |
| Set budget | - Work with business manager to finalize budgets - Use our budget template |  |
| Select and reserve venue | Remember to review: - A/V capabilities - Parking availability/restrictions, request through TTU parking if needed in advance - Other events occurring near space – will they conflict? - Accessibility – how will persons with disabilities enter the venue? - Send vendors location map - Included equipment with room rental - Security issues - Rain back up plan |  |
| Determine guest list | - Consider your target audience and key messages - When possible, research similar past event lists - Request alumni lists through External Relations team - Research guest travel arrangements and hotel options if needed |  |
| Research potential vendors | - All vendors MUST be or become an approved TTU vendor: See the set up process for new vendors - Review Texas Tech policies regarding contracts and procurement |  |
| Meet with Assistant Director of Events for consultation | - Submit event support request form 1st using this form - Review event details, needs, suggestions - Share all event marketing material requests, needs, and sending dates - Discuss potential communications plan - Discuss and development/donor or recruitment opportunities |  |
| Determine staffing needs for event check-in, set up, & tear down | - Send out calendar invites for shifts needed - Provide a volunteer job description/job duties doc |  |
| Consult with Development Office | - Review any legal questions for event - Request Anthology website from central, if needed |  |

4-6 Weeks Prior

| Task | Comments | Completed |
| --- | --- | --- |
| Develop a communications plan | - What is your event’s main message? - What media reaches your target audience? - Determine what channels to advertise and when is the best time to send messages. - Consult with the college’s Office of Marketing & External Relations for advice and inspiration. |  |
| Select & book caterer (Department/center responsibility) | - Do any of your guests have dietary restrictions? - Remember vegetarian options - Will you need linens from the caterer or other rental company? - Remember water for the speakers and/or bottled for guests, if applicable - Check with business manager of funding source/payment method needed and process |  |
| Update any website material | - Include common guest questions such as parking, dress code, and program schedule - Directions to event location |  |
| Add event to college events calendar and discuss other internal promotion opportunities | - Consider Tech Announce, Internal Insights, etc. - CHHS Events outlook calendar (internal only) |  |
| Contact Parking & Transportation | - Review the request form on TTU’s event parking requests web page |  |
| Schedule photographer or videographer if needed | - Request through this form |  |
| Select vendor for printed materials | - Common vendors: Slate Group, TTUHSC Printing Center, Advanced Graphix - Note: It is the department’s responsibility to place the order for all printed materials unless specifically requested through the Office of Marketing & External Relations. |  |
| Order any giveaways or speaker gifts |  |  |
| Supply all needed program, agenda, etc. information to designer for event materials | - Request and receive speakers’/VIPs’ bios and high-resolution photos if needed - Agenda schedule details - Program information |  |
| Order/send save-the-date cards or emails | - Ensure they are properly branded with the current TTU branding guidelines |  |

3-4 Weeks Prior

| Task | Comments | Completed |
| --- | --- | --- |
| Secure A/V needs for event | - Lighting & sound - Supplemental video needs - Powerpoint or slide show needs, if any - Coordinate additional mics in the audience for any Q&A needs - Ensure you have on-site A/V tech for event - Provide speakers with show flow document in advance |  |
| Request news release | - Consult with Office of Marketing & External Relations |  |
| Order plants/flowers | - Remember rental plants for staging and all floral needs |  |
| Edit all printed programs/materials | - Send edits to designer - Have multiple people proofread - Note: It is the department’s responsibility to place the order for all printed materials unless specifically requested through the Office of Marketing & External Relations. |  |
| Schedule supplemental staffing | - Ushers, crowd management, etc. |  |
| Send preliminary volunteer requests | - Student Ambassadors are great resources |  |
| Request participation of additional speakers | - Emcees, presenters, etc. - Always have someone introduce the President or other VIP |  |
| Order additional décor materials | - Flowers - Balloons - Pipe and Drape |  |
| Reserve additional set-up materials | - Rental chairs - Stage - Podiums - Tables - Easels - Coat rack - Heat lamps |  |

1-2 Weeks Prior

| Task | Comments | Completed |
| --- | --- | --- |
| Review printed materials with your designer | - Note: It is the department’s responsibility to place the order for all printed materials unless specifically requested through the Office of Marketing & External Relations. |  |
| Distribute flyers/emails advertising event |  |  |
| Finalize menu with caterer – send final head count |  |  |
| Finalize transportation logistics for VIPs and out-of-town guests |  |  |
| Release press announcements |  |  |
| Hold walk-through with major stakeholders/committee members to ensure all needs are met |  |  |

1 Week Prior

| Task | Comments | Completed |
| --- | --- | --- |
| Confirm staff/volunteers for each aspect of the event |  |  |
| Make parking and directional signs that can be created in-house | - Templates available through the Office of Marketing & External Relations |  |
| Finalize script for yourself or for VIPs/presenters | - Request scripts from all participants with a talking role to add into show flow document and ensure that speakers are within time restraints |  |
| Host volunteer training | - Email event roles in advance |  |

5-7 Days Prior

| Task | Comments | Completed |
| --- | --- | --- |
| Confirm participation with all VIPs/presenters. Send them updated event details, run of show, and talking points. |  |  |
| Create seating plans and room diagrams for assistance with set-up and day-of-event questions | - Ensure you follow correct protocol for head table seating - Create place cards for seated, if needed - Ensure you have back-up seating options available for changes within head table seating arrangements |  |
| Hold pre-event meeting with all significant stakeholders (vendors, managers of venue, key committee members and volunteers, etc.) |  |  |
| Do one last walk-through of venue |  |  |
| Ensure all printed materials/collaterals are assembled and correct |  |  |
| Make nametags/lanyards for attendees and extra plain ones for surprise guests | - If disposable, suggest Avery 8395 - Preferred template – Arial Bold, all caps |  |
| Stock “Event Day Survival Kit” full of needed items: pens, sharpies, tape, scissors, etc. |  |  |
| Confirm set-up/breakdown with all vendors |  |  |
| Send final information to participants, including directions, maps, last-minute details, etc. |  |  |
| Send completed Show Flow to speakers, VIPs, staff, volunteers, if not sent already |  |  |

1-2 Days Prior

| Task | Comments | Completed |
| --- | --- | --- |
| Create final to-do list to determine all tasks are complete |  |  |
| Ensure all appropriate contacts’ information is listed where you can easily retrieve it | - Recommend they are added to your phone for easy texting capabilities on event day |  |
| Reconfirm schedule with caterer |  |  |
| Set-up registration area, if possible, so you are prepared for the next day |  |  |
| Decorate/set up room early if you can |  |  |
| Display parking/directional signs |  |  |
| Gather all needed materials (name badge, notebook, etc.) |  |  |
| Deliver materials/equipment to venue site |  |  |

Day of Event

| Task | Comments | Completed |
| --- | --- | --- |
| Arrive early and do one last walk-through |  |  |
| Oversee vendor set-up |  |  |
| Remind all staff and volunteers of event duties | - Event contact info - FAQ answers for event - Check-in duties and times |  |
| Ensure all VIP materials are correctly labeled and in place | - Provide a program to VIPs so they know speaking or event order |  |
| Check all set-ups |  |  |
| Ensure waters and show flow docs are in podium |  |  |

Up to a Week After Event

| Task | Comments | Completed |
| --- | --- | --- |
| Send thank you notes |  |  |
| Handle invoices |  |  |
| Hold post-event meeting with key players |  |  |